Evaluation processes / Global Proposal (May 2013)

Portfolio

Over the entire life-cycle of the project	Activities Report    +    Post (lively) narrative or depiction	Ana Cortinas

Participant Evaluation Feedback

After every meeting or training session	Close and Open questions to gather opinions and suggestions	Ana Cortinas

Qualitative Evaluation

1. Initial / February 2013: 	Video recording with opinions (students, teachers and families)	Maribel
about ‘Meaningful’, ‘Creative’ and ‘Secure’ Use of ICT.

2. In progress / May-June 2013:	Group Reflection in each School and in local coordination group	Maribel & Evaluation 
following assessment guide. (Meant to make us aware of our 	Committee
processes /opportunity for establishing changes or adjustments)
International session: Second visit to Madrid May 2013 (short guide)	Maribel / Carolina

3. Final / May 2013	Not defined (yet)

Compulsory Steps:

Intermediate report / June 2013 	In standby until next week meeting with National Agency	Ana Cortinas

‘Products’ and others / June 2014	Not defined (yet)

Criteria Quantitative / Qualitative

School year 2013-2014	Numerical data gathered around defined criteria	Giacomo