**ACADEMIC YEAR 2013-2014 Curso 2013-2014**

| **ACTORS** | **Approx. starting date MM/YY** | **Activity description (organisation of an event, publication, study, website…)** | **Traducción en Español** | **Observaciones** |
| --- | --- | --- | --- | --- |
| **Similar activity is to be held in both partner regions** | September 2013 | **Teacher’s coordination meeting** | **Reuniones de coordinación de profesores** |  |
|  | ~~October~~ 2013  **November, 5-10** | **All partners meeting in partner region 2: PLANNING FOR ACADEMIC YEAR** | **Reunión general en Parma: Planificación para el curso académico 13-14** |  |
| **Similar activity is to be held in both partner regions** | October and November 2013 | **Teacher’s training** for all teachers in all schools  According to their own training needs related to the project development, as expressed in previous activities. | **Formación para los profesores de todas las escuelas**  Según las necesidades de cada uno, en relación con el desarrollo del proyecto, tal como se hayan venido recogiendo en actividades previas |  |
| **Similar activity is to be held in both partner regions** | December 2013 / January 2014 | **School communities’ sensibilization workshops.**  According to their own training needs related to the project development, as expressed in previous activities. | **Seminarios de sensibilización dirigidos a las comunidades educativas**  Según las necesidades en relación con el desarrollo del proyecto, tal como se hayan venido expresando en actividades previas |  |
|  | **January 2014, 21-25** | **Third Meeting in Madrid: for ”in process coordination”** | Tercera Reunión en Madrid para Coordinar los procesos en marcha |  |
| **Similar activity is to be held in both partner regions** | January / February / Mars 2014 | **Main curricular practices in schools, included in Lesson Plans.**  **Topic: *showing how to use ICT in a meaningful, creative and secure way for collaborative learning.***  Teachers involved in the project will propose to their group of students some **curricular activities**, focussing on the established topic.  A recompilation of works will be housed in Website. | **Practicas curriculares, incluidas en el curriculum.**  **Tema: *Mostrar cómo se pueden usar las TIC de forma significativa, creativa y segura, en procesos de aprendizaje en colaboración.***  Los profesores desarrollarán actividades curriculares, poniendo énfasis en el uso MCS.  Los trabajos se recopilarán en la página Web del Proyecto MCS |  |
|  | **April 2014, 28 y 29** | **Final Event in Madrid: Two Days Open Conference.**  **Open Retransmission.**  Teaching training Institutions and other schools and non-school institutions will be invited to attend to this Conference. It will be a privileged occasion to share outcomes, ‘good practices’, experiences, documents…  It’s meant to be a participatory event with presentations by teachers, students, parents… | **Evento final en Madrid: Dos días ¿? de actividad abierta a la comunidad educativa.**  **Retransmisión en EducaMadrid**  Será una oportunidad para compartir y debatir: resultados, buenas prácticas, experiencias, documentos…  Está pensado como un evento participativo, con la participación de profesores, estudiantes, padres… |  |
|  | **May 2014, 13-17** | **Meeting in partner region 2:**  **GLOBAL EVALUATION AND SUSTAINABILITY** | **Reunión en Parma**  **EVALUACIÓN GLOBAL Y SOSTENIBILIDAD** |  |
| Both partner regions, with the collaboration of all regional partners | June / July 2014 | **Final Report, documents, paperwork, conclusions…** | **Informe final, documentación, “papeleo” , conclusiones** |  |
|  | June / July 2014 | **Publication of results.** | **Publicación de resultados** |  |