Evaluation processes / Global Proposal (January 2014)

Portfolio

Over the entire life-cycle of the project	Activity Report    +    Post: lively narrative or description	Ana Cortinas

Participant Evaluation Feedback

After every meeting or training session	Closed and Open questions to find out opinions and suggestions	Ana Cortinas

Qualitative Evaluation

1. Initial / February 2013: 	Video recording with opinions (students, teachers and families)	Maribel
about ‘Meaningful’, ‘Creative’ and ‘Secure’ Use of ICT.

2. In progress / May-June 2013:	Group Reflection in each School and in local coordination group	Maribel & Evaluation 
following assessment guide. (Meant to make us aware of our 	Committee
processes /opportunity for establishing changes or adjustments)
First International session: Second visit to Madrid (May 2013)	Maribel / Carolina
Italian session: Second visit to Parma (November 2013)	Ana Díaz

3. Final / May 2014	Rubrics? A rubric is an attempt to communicate expectations of quality around
 a task. Proposal in next International Meeting (Madrid, January 2014)

Compulsory Steps:

Intermediate report / June 2013 	(Official procedure) Already sent to National Agency 	Ana Cortinas

‘Products’, ‘results’, ‘outcomes’ / June 2014	Not defined (yet). For Debate

Criteria Quantitative / Qualitative

School year 2013-2014	Numerical data gathered around defined criteria	Giacomo